# THE STATE UNIVERSITY OF ZANZIBAR

# SCHOOL OF EDUCATION

# Terms of Reference (ToR) for External Evaluator – RADIC Project Final Evaluation

## 1. Background

The Rehabilitation for All through Digital Innovations and New Competences (RADIC) project aims to strengthen digital rehabilitation capacity and collaboration in East Africa. Through partnerships among universities, rehabilitation practitioners, service users, and technology experts, RADIC has worked to enhance research, training, and service delivery using digital tools and innovations.(https://www.jamk.fi/en/project/radic). Since its inception, RADIC has promoted knowledge exchange, innovation, and multi-stakeholder engagement across the region. As the project concludes, the consortium seeks to engage an External Evaluator to conduct a comprehensive final evaluation of performance, results, and sustainability.

## 2. Purpose of the Evaluation

- The main purpose of this evaluation is to provide an independent and objective assessment of the project’s overall achievements and lessons learned.

- The evaluation will generate evidence to inform future programming, strengthen accountability, and support knowledge sharing among partners and stakeholders. Specifically, the review will:

- Determine how effectively RADIC achieved its objectives.

- Assess the impact of RADIC’s interventions on stakeholders and beneficiaries.

- Identify lessons learned and good practices for replication or scale-up.

- Provide recommendations for sustainability beyond the project’s lifetime.

## 3. Evaluation Objectives

  - Relevance: Assess the extent to which the project’s objectives and activities addressed key rehabilitation and digital innovation needs in East Africa.

  - Effectiveness: Determine how well the project achieved its expected outcomes and outputs.

  - Efficiency: Examine the use of financial, human, and technical resources to deliver results.

  - Impact: Evaluate the broader influence of the project on rehabilitation practice, research, and policy.

  - Sustainability: Assess the likelihood that project results and partnerships will continue after completion.

## 4. Scope of the Evaluation

  - The evaluation will cover the entire project duration from inception to February 2026.

  - It will review all project components, including completion of work packages, capacity building, digital innovation, knowledge exchange, and stakeholder engagement.

  - The evaluation will consider the geographical coverage, institutional partners, and direct and indirect beneficiaries.

Key tasks will include:

- Review of project documents, reports, and monitoring data.

- Interviews and focus group discussions with key stakeholders.

- Analysis of project performance indicators.

- Collection of feedback from mid-term conference participants.

## 5. Methodology

- The evaluation should employ mixed methods, integrating both qualitative and quantitative approaches.

- The evaluator is expected to propose a detailed and participatory methodology.
Possible methods include:

- Desk review of project documents and reports.

- Semi-structured interviews with partners, beneficiaries, and policymakers.

- Online or virtual surveys where appropriate.

- Case studies showcasing successful innovations or partnerships.

- Validation of findings through stakeholder consultation.

## 6. Deliverables

- Inception Report – outlining understanding of the assignment, methodology, tools, and timeline (within 2 weeks of contract signing).

- Draft Evaluation Report – presenting preliminary findings, conclusions, and recommendations.

- Final Evaluation Report – incorporating feedback from the RADIC Steering Committee and partners.

- Presentation of Findings – to be delivered during a virtual or in-person dissemination session.

## 7. Proposed Timeline

The evaluation will take place between February and April 2026 to align with the project closure schedule.

| Phase | Activity | Timeline |
| --- | --- | --- |
|  | Inception phase and document review | 15th January 2026 |
|  | Data collection and analysis | 01st February 2026 |
|  | Draft report submission | 15th February 2026 |
|  | Validation and dissemination workshop | 25th February 2026 |
|  | Final report submission | 10th March 2026 |

## 8. Qualifications and Experience

a. The evaluator (individual or firm) should possess:

- An advanced degree in Monitoring and Evaluation, Quality evaluation, or any other related field.

- At least five (5) years of experience conducting evaluations in health, rehabilitation, or digital innovation sectors.

- Proven understanding of disability inclusion, digital health and technology-based development programs.

- Strong analytical, writing, and communication skills.

- Familiarity with the East African context is an added advantage.

- Experience and/knowledge of ERASMUS Project and Guidelines.

## 9. Management and Reporting

- The evaluator will report directly to the RADIC Project Steering Committee through the Project Manager.

- Cost and logistics wil be fixed on contract.

- All deliverables must be reviewed and approved by the Steering Committee before finalisation.

## 10. Ethical Considerations

a. The evaluation must adhere to recognized ethical standards, ensuring:

- Respect for diversity and cultural sensitivity.

- Transparency in reporting and data analysis.

- All data gathered and received should be respected and confidential

## 11. Application Procedure

a. Interested consultants or firms should submit the following documents:

- Technical proposal outlining understanding of the ToR, proposed methodology, and work plan.

- Financial proposal detailing professional fees and related costs.

- Curriculum Vitae (CV) of key personnel involved.

b. Applications should be submitted by 10th Janurary 2025 to

Dean

School of Education

The State University of Zanzibar

soe@suza.ac.tz

with the subject line:

“RADIC Final Evaluation – External Evaluator Application.”